## Features
Phase | Feature ID | Feature Name | Area | Status | Description | Tables Touched | Endpoints Added | Tests | PR(s) | Live Mode Gate
Phase 0 | F0.1 | Smoke test + audit extractors | Tooling | Live + UI wired | scripts/audit/{smoke_test.sh, extract_endpoints.py, extract_schema.py} regenerate inventory CSVs and probe app health. | — | — | Run locally | Audit drop-in (pre-#1) | —
Phase 0 | F0.4 | server/lib/req.ts type-safe extractors | Lib | Live + UI wired | paramStr/paramInt/headerStr/queryStr handle Express 5.x widened param/header types. | — | — | Used everywhere | — | —
Phase 0 | F0.5 | Pricing engine extracted to services/pricing.ts | Service | Live + UI wired | computeDealTotalsFromLines + reconcileLine + recalcPricingFromScope + persistDealTotals + backfillDealTotals. | — | — | calc-parity golden test | — | —
Phase 0 | F0.6 | ESLint flat config + Prettier | Tooling | Live + UI wired | eslint.config.js (ESLint 9 flat); 0 errors / ~120 warnings baseline. | — | — | npm run lint | — | —
Phase 0 | F0.10 | recalcPricingFromScope idempotency | Service | Live + UI wired | Back-derive standardRate from rate/factor when empty; persist on update so repeat runs don't compound the T&M factor. | pricing_lines | — | tests/pricing/recalc-idempotency.test.ts | — | —
Phase 0 | F0.11 | flushPendingEdits util (macOS onBlur fix) | UI Lib | Live + UI wired | document.activeElement?.blur() fired on onMouseDown so wizard nav buttons commit pending input edits before unmount. | — | — | Manual | — | —
Phase 1 | F1.1 | Multi-entity worksheets | Schema + UI | Live + UI wired | deal_entities table; tabs in DealDetail Scope step let one deal model 4+ entities (e.g. 1040 + 1120 + 1065 + 1120S) each with own scope/pricing rollup. | deal_entities (NEW) | GET/POST /api/deals/:dealId/entities, GET /entities/:id/totals | tests/integration/multi-entity.test.ts | F1.1.* chain | —
Phase 1 | F1.1.1 | scope_items entity_id + per-entity unique index | Schema fix | Live + UI wired | deal_scope_items.entity_id nullable + (deal_id, entity_id, scope_item_id) unique index lets each entity carry its own copy of a scope item. | deal_scope_items | — | tests/integration/scope-per-entity.test.ts | PR #53 | —
Phase 1 | F1.2 | Assembly expansion engine | Schema + Service + UI | Live + UI wired | assembly_templates + assembly_components; AssemblyExpansionService uses math.js sandboxed AST for quantity formulas; AssemblyPicker UI on Scope step. | assembly_templates, assembly_components (NEW) | GET /api/assemblies, GET /:id/components, POST /:id/expand, POST /scope-items/from-assembly | tests/assembly/* | F1.2.* chain | —
Phase 1 | F1.3 | Batch renewal processing | Schema + Service + UI + Worker | Live + UI wired | batch_renewal_jobs + items + adjustment_rules; BatchRenewalService runs variance math + adjustment rules; admin page at /admin/batch-renewals; Python Celery+Redis worker scaffolded. | batch_renewal_jobs, batch_renewal_items, batch_adjustment_rules (NEW); services/batch-processor/ | GET/POST /api/batch-renewals, /:id/start, /:id/items, /api/batch-adjustment-rules | tests/batch/*, tests/integration/batch-renewals.test.ts | F1.3.* chain | —
Phase 1 | F1.4 | DDD Strangler-Fig: Deal aggregate | Domain | Live + UI wired | @dealpad/domain (Money, Percentage, Deal, DealStatus, events) + @dealpad/application (SubmitDealService, ApproveDealService, RejectDealService) + @dealpad/infrastructure (DrizzleDealRepository, InProcessEventBus, OutboxDispatcher). POST /submit + /approvals routes migrated. | domain_events_outbox (NEW) | POST /api/deals/:id/submit, POST /:dealId/approvals, PATCH /api/approvals/:id (refactored) | tests/domain/*, tests/application/*, tests/integration/{submit,approve}-deal.test.ts | F1.4.* chain | —
Phase 2 | F2.1 | Intelligence Engine (pgvector k-NN) | Schema + Service + Routes | Live + UI wired | deals.fingerprint JSONB + deals.embedding vector(1536); IntelligenceEngine.findSimilar uses pgvector <-> operator. Heuristic mode default; openai/azure stubbed. | deals | POST /api/ai/deal-similarity (refactored), POST /api/admin/intelligence/backfill, POST /api/deals/:id/intelligence/recompute | tests/intelligence/*, tests/integration/{intelligence,deal-similarity}.test.ts | F2.1.* chain | openai/azure modes need API keys
Phase 2 | F2.2 | Budget-to-actuals monitoring | Schema + Service + Routes + UI | Live + UI wired | budget_actuals + budget_alerts; BudgetMonitorService with thresholds (over_budget ≥110%, near_budget ≥90%, burn_rate ≥15%). UI at /deals/:id/budget. | budget_actuals, budget_alerts (NEW) | GET /api/deals/:id/budget-actuals, /:id/budget-alerts, POST /:id/budget/recompute, POST /api/admin/budget/monitor-all, PATCH /api/budget-alerts/:id, GET /api/budget-alerts/open-count | tests/budget/*, tests/integration/budget-*.test.ts | F2.2.* chain | Celery beat cron not yet wired
Phase 2 | F2.3 | Time tracking + AI suggest | Schema + Service + Routes | Live + UI wired | time_entries table; full CRUD + /api/time/suggest with deterministic-simulated mode. BudgetMonitor prefers time-entry sums when present. | time_entries (NEW) | GET/POST /api/deals/:id/time-entries, /:id/time-entries/summary, PATCH /DELETE /api/time-entries/:id, POST /api/time/suggest | tests/time-entry/*, tests/integration/{time-routes, budget-from-time-entries}.test.ts | F2.3.* chain | VOICE_MODE=graph (Microsoft Graph) stubbed
Phase 2 | F2.4 | Alternative fee arrangements | Schema + Service + UI | Live + UI wired | deals fee_arrangement (T&M ¦ fixed ¦ capped ¦ contingent ¦ retainer ¦ hybrid) + 6 amount/percent columns; applyFeeArrangement projection; FeeArrangementPicker UI on Pricing step. | deals | GET /api/fee-arrangements, GET /api/deals/:id/fee-projection, PATCH /api/deals/:id/fee-arrangement | tests/pricing/feeArrangements.test.ts, tests/integration/fee-arrangement-routes.test.ts | F2.4.* chain | —
Phase 3 | F3.1 | Real-time collaborative scoping (foundation) | Schema + Service | Foundation only | collaboration_sessions table for room allocation + Yjs update-vector durability. WebSocket gateway + CRDT integration deferred. | collaboration_sessions (NEW) | GET /api/collab/document-keys, POST /api/deals/:id/collab/sessions, GET /:id/sessions/:key, POST /snapshot + /presence | tests/integration/collab-sessions.test.ts | F3.1.1 (PR #39) | yjs + ws packages + DealDetail refactor
Phase 3 | F3.2 | Client self-service portal (magic-link) | Schema + Service + Routes | Foundation only | portal_invites table; SHA-256 hashed tokens (plaintext never persists); /api/portal/* with token-gated middleware separate from persona RBAC. | portal_invites (NEW) | GET/POST /api/deals/:id/portal-invites, DELETE /api/portal-invites/:id, GET /api/portal/{me,deal,scope} | tests/portal/*, tests/integration/{portal-auth, portal-routes}.test.ts | F3.2.1 + F3.2.2 (PR #37, #38) | Email/SMS delivery not wired
Phase 3 | F3.3 | Scope creep detector (heuristic) | Schema + Service + Routes | Foundation only | scope_creep_signals + ScopeCreepDetector with 5 rules (scope_growth, change_order_density, burn_rate, margin_drift, stale_no_progress). ML score plugs into evaluate() seam. | scope_creep_signals (NEW) | GET /api/deals/:id/scope-creep, POST /:id/scope-creep/scan, PATCH /api/scope-creep/:id | tests/creep/*, tests/integration/scope-creep-routes.test.ts | F3.3.1 (PR #40) | Trained ML model needs labeled dataset
Phase 3 | F3.4 | Voice-to-scope | Schema + Service + Routes | Foundation only | voice_transcripts table; token-overlap heuristic ranks scope_catalog matches; apply-to-deal flow. Audio bytes never persist. | voice_transcripts (NEW) | GET/POST /api/deals/:id/voice-transcripts, POST /api/voice-transcripts/:id/process, /:id/apply | tests/voice/*, tests/integration/voice-routes.test.ts | F3.4.1 (PR #41) | VOICE_MODE=azure (Speech) needs Cognitive Services keys
Phase 3 | F3.5 | Slack/Teams native apps | — | Deferred | Bolt.js Slack app + slash commands; not started. | — | — | — | — | Tenant OAuth + Bolt.js setup
Phase 3 | F3.6 | Rate optimization (heuristic) | Schema + Service + Routes | Foundation only | rate_optimization_runs + RateOptimizerService with capacity + velocity + margin signals (caps at +15%/-10%). ML model plugs into evaluate() seam. | rate_optimization_runs (NEW) | GET/POST /api/rate-optimization/runs, PATCH /api/rate-optimization/runs/:id | tests/rate-opt/*, tests/integration/rate-optimization-routes.test.ts | F3.6.1 (PR #42) | LTV + seasonality model needs training data
Phase 4 | F4.1 | pgvector RAG | Service | Live + UI wired | Already shipped via F2.1 — IntelligenceEngine.findSimilar uses pgvector cosine similarity. | deals | POST /api/ai/deal-similarity | tests/intelligence/* | F2.1.* chain | —
Phase 4 | F4.2 | ml-service Python scaffold | Service (Python) | Foundation only | FastAPI service hosting /effort-estimator + /margin-optimizer in heuristic mode; sklearn / azureml modes stubbed. | — | GET /health, POST /effort-estimator, POST /margin-optimizer (FastAPI; localhost:8000) | Manual: uvicorn + curl /health | F4.2.1 (PR #50) | Trained model + ML_MODE=sklearn¦azureml
Phase 4 | F4.4 | llm.ts client abstraction | Service | Foundation only | complete() + completeStructured() with simulated default + anthropic/openai/azure_openai stubs. Zod-validated structured output. Auto-instrumented via withAiTelemetry. | — | — | tests/llm/llm.test.ts | F4.4.1 (PR #47) | LLM_PROVIDER=anthropic¦openai needs API keys
Phase 4 | F4.4.2 | risk-summary (UC-5) via llm.ts | Routes | Live + UI wired | POST /api/ai/risk-summary now flows narrative + keyMessage + approvalLikelihood through llm.completeStructured. Heuristic baseline preserved; LLM enriches. | — | POST /api/ai/risk-summary (refactored) | tests/integration/risk-summary-llm.test.ts | F4.4.2 (PR #48) | Real LLM call gated on LLM_PROVIDER + key
Phase 4 | F4.4.3 | margin-advisor (UC-3) via llm.ts | Routes | Live + UI wired | POST /api/ai/margin-advisor adds narrative + callToAction via llm.completeStructured. Suggestion math stays heuristic. | — | POST /api/ai/margin-advisor (refactored) | tests/integration/margin-advisor-llm.test.ts | F4.4.3 (PR #49) | Real LLM call gated on LLM_PROVIDER + key
Phase 4 | F4.5 | AI telemetry middleware + dashboards | Schema + Middleware + Routes | Live + UI wired | ai_telemetry table; recordAi + withAiTelemetry capture token counts, latency, errors, cost USD. Dashboard summary endpoint computes p95 + per-operation cost rollups. | ai_telemetry (NEW) | GET /api/ai-telemetry, GET /api/ai-telemetry/summary | tests/ai-telemetry/*, tests/integration/ai-telemetry-routes.test.ts | F4.5.1 (PR #46) | Dashboard UI page is a chore PR
Operational | fix.dynamics-seed | Dynamics seed skips test-fixture deals | Bugfix | Live + UI wired | Excludes __test_* / DL-TEST-* deals from the on-boot opportunity-creation sweep. Stops the dashboard's Latest Opportunities panel from filling with synthetic rows. | — | — | — | PR #51 | —
Operational | fix.auto-seed-primary-entity | Every deal-create path auto-seeds Primary Entity | Bugfix | Live + UI wired | ensurePrimaryEntity helper called from POST /api/deals, /clone, /agent-draft, and Dynamics import. Closes the F1.1 backfill-only gap for mid-session deals. | — | — | tests/integration/deal-create-primary-entity.test.ts | PR #52 | —
Operational | fix.healthz | Public /healthz for Render healthcheck | Bugfix | Live + UI wired | Bypasses persona-RBAC so deploy gates don't 401. Returns 200 with no DB hit. | — | GET /healthz | — | PR #59 | —
Operational | deploy | Render + Neon deployment | Infra | Operational/infra | render.yaml Blueprint + Dockerfile + docs/deployment.md. Live at https://dealpad-demo.onrender.com (Starter + Neon Launch). | — | — | Smoke probe via /healthz + /api/dashboard/summary | PRs #55, #56, #57, #58, #59 | —

## Glossary
Column | Meaning
Phase | Refactor phase per docs/refactoring/BACKLOG.md (0=audit/tooling, 1=multi-entity foundation, 2=intelligence/budget/time/fees, 3=moat builders, 4=AI production).
Feature ID | Stable ID used in commit messages, branch names, and PR titles. Sub-IDs (e.g. F1.4.2) denote slices of a larger feature.
Feature Name | Short human-readable label.
Area | Where the feature touches: Schema / Service / Routes / UI / Lib / Tooling / Domain. Multi-area features list all.
Status | Live + UI wired = end-to-end production-ready including UI surfaces. Foundation only = schema/service/routes shipped; UI or live-mode wiring pending. Deferred = intentionally not started this cycle. Operational/infra = deployment, ops, or bugfixes.
Tables Touched | DB tables created or modified. (NEW) marks tables introduced by the feature.
Endpoints Added | REST endpoints introduced or refactored. Use docs/audit/api_inventory.csv for the authoritative list.
Tests | Test files exercising the feature. Suite total: 500+ tests as of 2026-05-04.
PR(s) | Pull request numbers on github.com/dhan99/NextGenPricing2. Multi-PR features list the chain.
Live Mode Gate | What's needed to flip a Foundation feature to Live (API keys, training data, integrations).